## Agile Project Plan
AGILE PROJECT PLAN
| PROJECT NAME | Professor | START DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE | P.Proposal (due week 7), Progress Report (due week 9), Live Presentation (due Week10), Final Report (due after week 10)
| IST 707 Final Project | Jeremy Bolton | 2020-07-17 |  | 0% |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Project Proposal | Google Doc made 8/9/2020 | Team | 2020-07-25 | 2020-08-11 | 17 | Done | Submission on 8/11/2020
| Select Data Set | Heart Attack: https://www.kaggle.com/nareshbhat/health-care-data-set-on-heart-attack-possibility?select=heart.csv | Team | 2020-07-17 | 2020-07-22 | 5 | Completed | Next Meeting July 25, 2020
| Define the problem | Data Question | Team | 2020-07-25 | 2020-07-25 | 0 | Completed | Who is more likely to be in higher risk of getting a heart attack?
| Clean data & EDA | See R Script. | Team | 2020-07-24 | 2020-07-25 | 1 | Completed | Initially, 303 records and 14 attributes. There was one duplicate. Changed some attributes from numerical to nominal. Changed the name of one calumn (age). Discretized the column 'age'. Decoded two attributes.
| ARM | See R Script. | Team | 2020-07-25 | 2020-07-31 | 6 | Completed
| Clustering |  | Team | 2020-07-25 | 2020-08-11 | 17 | In Progress
| Decision Tree | See R Script. | Team | 2020-07-25 | 2020-07-31 | 6 | Completed
| Naïve Bayes |  | Team | 2020-07-17 | 2020-07-17 | 0 | Not Started
| SVM |  | Team | 2020-07-17 | 2020-07-17 | 0 | Not Started
| Text Mining (optional) |  | Team | 2020-07-17 | 2020-07-17 | 0 | Not Started
| Written Report | Google Doc made 7/25/2020 | Team | 2020-07-25 | 2020-07-17 | -8 | Not Started
| PPT Presentation |  | Team | 2020-07-17 | 2020-07-17 | 0 | Not Started

## Agile Project Plan - BLANK
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
Sprint 1
Feature 1
Feature 2
Feature 3
Sprint 2
Feature 4
Feature 5
Feature 6
Sprint 3
Feature 7
Feature 8
Feature 9